## Agenda topics
INTERNATIONAL CANOE FEDERATION
Topics for Discussion at the ICF Board Meeting March 2017
This is a working document for the ICF Board of Directors and takes account the major topics and project undertaken by the ICF in the current Strategic Plan period 2017-2020. It will be used as the main part of the Agenda and form the basis for the minutes of the meeting.
BoD Discussion and Decision Issues - Manchester March 2017
Discipline | Topic | Description of item | Request (info, decision, ongoing) | Importance (High/med/low) | Who has responsibility | Any intermediary tasks to complete | Deadline
ICF | Doping situation | Update on Russian Doping cases and Moldovan case. | Decision by BoD required | High | Anti-Doping Panel | Explore possible legal avenues and decide actions | April 2017
ICF | HQ Staffing | Update on ICF Staffing | Endorsement of BoD | Medium | Secretary General | Interviews and selection process | May 2017
ICF | SUP | Update on Stand Up Paddling and ongoing dispute with International Surfing Association - Presentation of situation | Discussion, decision | High | ICF President, VP Thomas Konietzko, Secretary General | Legal advice, Communication strategy, potential legal strategy to CAS | Ongoing
ICF | Global Situational Study on Canoe | Presentation of the initial results from market survey by Nielson marketing | Discussion | Low | Secretary General | Assessment of data and analysis of results | Ongoing
ICF | ICF Conflict of Interest Policies | Confirm BoD agree policy and then individually sign the form | BoD Approval | High | ICF Secretary General, Paracanoe Chair | Presentation of documents from Governance file | Ongoing
ICF | Technical / General rules | General/Technical Rules clarification | Discussion | Medium | Board, European President | Analysis of the Rule Books | Ongoing
ICF | Congress | Rules for Proxy Votes etc and Nationality of delegates and Quorum decision date | Discussion | low | Board. European President | None | Ongoing
ICF | TV broadcasting | Determine future media strategy for TV broadcasting | Information and discussion | Low | Media manager, Secretary General, Andrej Jelenc | None | Onging
ICF | Governance | Discussion on roles and responsibilities of all ICF Stakeholders | Discussion and decision | High | Board, Secretary General | Governance proposal | Ongoing
ICF | Governance Operating Procedures | Discussion on operating procedures such as Ethics Committee, Financial Commission etc | Discussion and decision | Medium | Board, Secretary General | Governance proposal | Ongoing
ICF | Development Programme | Analysis of the current status of the Programme. Determine the new development strategy | Discussion, decision | High | VP- Cecilia Farias | Discussion with discplines and continents. Presentation of proposal to Board and action plan. | April 2017
Olympic Disciplines | Olympic Programme 2020 | Final confirmation of the Olympic Programme for Canoeing 2020 | Discussion and approval | High | Chairs, VPs and Secretary General | Analysis of Statistics from Rio 2016 and potential changes to the Qualification Systems | April 2017
Dragon Boat | ICF-IDBF collaboration | Establish a working relationship between ICF & IDBF for future World Championships | Ongoing | Low | VP- Thomas Konietzko, Technical Chair | Meeting with IDBF being arranged | April 2017
Dragon Boat | ICF competitions | Proposal of Dragonboat World Series | Ongoing | low | Technical Chair, Secretary General | Assess proposal, meetings with agency and discuss with NFs for teams | August
Dragon Boat | ITO appointments | ITOs for 2017 ICF Dragon Boat Club Crew World Championships | Decision by BoD required | Medium | Technical Chair | Table of ITOs presented to BoD | April 2017
Canoe Freestyle | Judges Seminar | Proposal for Judges seminar 2017 | Discussion and decision | Medium | Technical Chair | Proposal of project including costs | April 2017
Canoe Freestyle | Freestyle in a box | Presentation of concept | Presentation | Low | Technical Chair | Presentation of proposal | April 2017
Canoe Sprint | Events for 2017 | Events with new formats | BoD Approval | High | Technical Chair |  | April 2017
Canoe Sprint | Competition distribution | Worldwide distribution of events | information only | Low | Technical Chair | Part of CSPC Strategy Plan | April 2017
Canoe Sprint | ITO selections | 2017 W. Cups, World Jr./U23 Champs & World Champs | BoD Approval | High | Technical Chair | None | April 2017
Canoe Sprint | ITO exams / seminars | Scheduling of exams | information only | Medium | Technical Chair | Part of CSPC Strategic Plan | April 2017
Canoe Sprint | Canoe Sprint Strategy | Strategic Plan for Canoe Sprint 2018-2024 | Discussion and approval | Low | Chair, VP and Secretary General | Analysis of data, evaluation of previous editions, discussions with stakeholders | End of 2018
Canoe Sprint | Development | Encourage Women's participation in Canoe events | Discussion | Low | Oluode Olbunmi | Draft incentives and policy | 2019
COPAC | Development Actvitiy | Central America Canoe Development | BoD Approval | Medium | Victor Ruiz and the Development Chair | Jamica development programme, Coaching Symposium level 1 and 2. | May 2017
ASIA | Development | Claims from NF that they receive no information regarding visits from development. ACC/NF not notified or CC'd in communication with individual athletes. | Discussion | Low | Asia President and Development Chair | None | April 2017
ASIA | Membership Fee | Membership Fees for countries should be determined by activity, not the financial situation of the country. Some countries are in a "downward spiral" preventing them from beginning canoeing activities. | Discussion | Low | Asia President, Treasurer, Secretary General | None | 2019
ASIA | India Slalom Course | Information re: Slalom Course at Maheshwar Indore, India. This is a natural river course satisfying International standards. Indian Kayak Canoe Association wants to open for training. | Information | Low | Slalom Chair, Development | None | Ongoing
Ocean Racing | ICF Calendar | Approval of the 2018 World Cups 2018 | BoD Approval | Medium | Technical Chair | None | April 2017
Ocean Racing | ICF Calendar | Reopen the bids considering the Congress decision on the Rules | BoD Approval | High | Technical Chair, ICF HQ | send formal invitation for 2019, 2020, 2021 World Cup and 2020, 2021 World Champioships | April 2017
Ocean Racing | ICF Rules | Overlook the 2 athletes quota per countries and allow open entries in all events in the World Championships 2017, only condition being approved by the NF | BoD Approval | High | Technical Chair | None | April 2017
Ocean Racing | Website | Implement the Ocean Racing World Ranking inside ICF website | BoD Approval | High | ICF HQ | Consultation with organisers and CORC | April 2017
Canoe Slalom | 2017 CSL Senior World Championships | Detailed competition schedule for World Championships | BoD Approval | High | Technical Chair | Presentation of proposal | April 2017
Canoe Slalom | 2017 Jun /U23 World Championships | Detailed competition schedule amended | BoD Approval | High | Technical Chair | Presentation of proposal | April 2017
Canoe Slalom | Extreme Canoe slalom Rules | Provisional Extreme Canoe slalom Rules, Chapter VIII of 2017 Canoe slalom Rules | BoD Approval | High | Technical Chair | For the 2017 World Cup season and first official Extreme Canoe Slalom World championships | April 2017
Canoe Slalom | Extreme Slalom | Provided status of Extreme Slalom events at the World Cup and international events | Information | Low | Technical Chair, Secretary General, andrej Jelenc | None | Ongoing
Canoe Marathon | 4-year Strategic Operation Plan | Approving the plan | BoD Approval | High | Technical Chair | Plan presented with the report documents | 2017
Canoe Marathon | ITOs | Approving recommended ITOs for 2017 World Championships | BoD Approval | High | Technical Chair | List presented with the report documents | April 2017
Canoe Polo | 2017 World Games | To approve Jury and Officials | BoD Approval | High | Technical Chair | None | April 2017
Canoe Polo | 2017 World Games | To allocate ICF HQ Media Person to World Games. | BoD Approval | Medium | ICF Secretary General | None | April 2017
Canoe Polo | 2018 World Championships | To approve Eva Lindmark as ICF Technical Delegate for Canada | BoD Approval | Medium | Technical Chair | None | April 2017
Canoe Polo | 2018 World Championships | Request the purchase of 10 x Kayaks/sets of equipment to a maximum of 10,000 Euros Note: This was abandoned for the 2016 World Championships/monies not spent due to inappropriate disclosure of confidental quotations. | BoD Approval | Medium | Technical Chair, Development Chair, Secretary General | Description of previous agreements and issue with Iast World Championships | December 2018
Canoe Polo | 2018 World Championships | To discuss and fix the dates for the 2018 ICF Canoe Polo World Championships | BoD Approval | High | ICF/ACC | None | April 2017
Paracanoe | 2017-2020 PC Strategic Plan | Set Paracanoe Strategic Plan for 2017-20 | BoD Approval | High | Paracanoe Chair | Presentation of proposal | April 2017